## Teams
Development Team & Requirements | Label
Software Platform/Web Development | SRS
Web/Mobile/Browser App | WRS
Virtual Video/Control Platform | VRS
Firmware Development | FRS
Mechanical Development | MRS
AI/ML Platform Development | AIML

## User Journey
Step # | Cube # | User Journey / Workflow
1.1 | Cube 1 (1,1,1) | Moderator defines the session objective, scope, participant roles, governance rules, questions, and polling format (single-round or multi-cycle).
1.2 | Cube 1 (1,1,1) | System creates a unique session instance, generates a secure session ID, QR code, and shareable access link for participants.
2 | Cubes 2–3 (1,1,2 / 1,1,3) | Users (participants) join the session via QR code or link and submit responses using text or voice, anonymously or identified as configured.
3 | Cubes 4–5 (1,2,1 / 1,2,2) | Moderator opens and closes polling windows; System validates inputs, timestamps submissions, encrypts data, and stores responses securely.
4 | Cube 6 (1,2,3) | System processes collected responses through AI pipelines to generate themes, clusters, summaries, and confidence indicators.
5 | Cube 7 (1,3,1) | Users review generated themes and submit prioritization rankings asynchronously or in real time.
6 | Cube 7 (1,3,1) | System aggregates rankings, computes ordered priorities, and attaches confidence and metadata for transparency.
7 | Cubes 7–8 (1,3,1 / 1,3,2) | Leads / Developers review prioritized outcomes, incorporate participant feedback, apply justified overrides if required, and confirm final decisions.
8 | Cube 9 (1,3,3) | System generates reports and exports, logs engagement and contribution metrics, calculates SoI Trinity Tokens (♡, 웃, ◬), and records activity for analytics and future simulations.
9 | Cube 10 (2,2,2) | Leads / Developers or the System enter simulation mode to check out individual cubes, test optimized code paths, compare performance metrics (latency, scale, cost), and either approve improvements for production or iterate further—preparing for future AI self-optimization.

## User Stories + Needs
User Stories | POC | Alpha | MVP1 | MVP2 | MVP3 | CRS # | Customer Needs | Note + VOC Comments
MVP 1.0 — QR Code & Session Access (Core)
As a Moderator, I want to create a polling session and generate a secure session link and QR code so participants can join instantly. |  |  | ● |  |  | CRS-01 | Fast, simple session creation with minimal setup overhead. | “I don’t want to explain how to join — it should just work instantly.”
As a User, I want to join a polling session via QR code or link without authentication friction so I can participate immediately. |  |  | ● |  |  | CRS-02 | Zero-friction access from any device. | “If I have to log in, half the room won’t participate.”
As the System, I want to generate unique, collision-free session IDs bound to QR codes so sessions cannot be spoofed or duplicated. |  |  | ● |  |  | CRS-03 | Trust that sessions are secure and not hijacked. | Enterprise buyers expect this as baseline security hygiene.
As the System, I want to validate QR-based access and block expired or invalid sessions so unauthorized joins are prevented. |  |  | ● |  |  | CRS-04 | Protection against misuse and accidental reuse. | “We don’t want old links floating around and confusing people.”
MVP 1.0 — Poll Control & Text Input
As the System, I want to support anonymous and identified participation modes so Moderators can choose the right privacy level. |  |  | ● |  |  | CRS-05 | Psychological safety and flexibility by context. | Anonymity increases honesty; identity increases accountability.
As a Moderator, I want to open and close polling sessions deliberately so responses are collected only during the defined window. |  |  | ● |  |  | CRS-06 | Clear control over when feedback is captured. | “I don’t want late answers changing the outcome.”
As a User, I want to submit text-based responses to polling questions so I can clearly express ideas and feedback. |  |  | ● |  |  | CRS-07 | Simple, reliable way to contribute ideas. | Text is the lowest-barrier input method for most users.
As the System, I want to securely store all responses with timestamps and encryption so integrity and compliance are preserved. |  |  | ● |  |  | CRS-08 | Confidence that data is safe and auditable. | Required for enterprise, government, and regulated industries.
MVP 1.0 — AI Theme Generation & Review
As the System, I want to cluster responses into meaningful themes using AI so large volumes of input become understandable. |  |  | ● |  |  | CRS-09 | Turn chaos into clarity at scale. | “We get hundreds of comments — no human can read them all.”
As a User, I want to view summarized themes generated from group input so I understand collective patterns. |  |  | ● |  |  | CRS-10 | Shared understanding of group sentiment. | Builds alignment and reduces repetitive discussion.
MVP 1.0 — Ranking & Export
As a User, I want to rank themes after polling closes so I can express priorities. |  |  | ● |  |  | CRS-11 | Ability to influence outcomes, not just comment. | Ranking feels more meaningful than voting yes/no.
As the System, I want to aggregate rankings deterministically so outcomes are fair and reproducible. |  |  | ● |  |  | CRS-12 | Confidence that results are objective and consistent. | “We need the same inputs to produce the same outputs.”
As a Lead/Developer, I want to review ranked priorities with metadata so decisions are evidence-based. |  |  | ● |  |  | CRS-13 | Context behind decisions, not just final numbers. | Leaders need defensible rationale for choices.
As the System, I want to export session results in CSV format so outcomes can be reused externally. |  |  | ● |  |  | CRS-14 | Easy integration with existing tools and workflows. | “If I can’t export it, it didn’t happen.”
MVP 2.0 — Voice, Live Collaboration & Analytics
As a User, I want to submit responses using voice instead of typing so participation is faster and more natural. |  |  |  | ● |  | CRS-15 | Lower barrier to participation in live settings. | Especially valuable for mobile and accessibility use cases.
As a Moderator, I want to enable live prioritization during sessions so consensus forms in real time. |  |  |  | ● |  | CRS-16 | Faster decision-making during live meetings. | “We want decisions before the meeting ends.”
As a User, I want to see real-time ranking updates so collaboration feels responsive. |  |  |  | ● |  | CRS-17 | Immediate feedback that my input matters. | Live updates increase engagement and trust.
As the System, I want to support real-time updates via WebSockets so live sessions remain synchronized. |  |  |  | ● |  | CRS-18 | Stable, low-latency collaboration experience. | Technical requirement to support live interaction at scale.
As the System, I want to track engagement and participation metrics so contribution quality is measurable. |  |  |  | ● |  | CRS-19 | Insight into who participated and how deeply. | Buyers want to measure engagement, not just outcomes.
MVP 3.0 — Deep Dives, Governance & Tokens
As a Moderator, I want to initiate deep-dive polling cycles so complex topics can be explored iteratively. |  |  |  |  | ● | CRS-20 | Structured exploration of complex decisions. | “One round is never enough for hard problems.”
As a User, I want to participate in follow-up deep-dive cycles while preserving context so prior input remains relevant. |  |  |  |  | ● | CRS-21 | Continuity across decision phases. | Losing context is a major frustration in workshops.
As a Lead/Developer, I want to override rankings with documented justification so accountability is preserved. |  |  |  |  | ● | CRS-22 | Balance between group input and leadership responsibility. | Leaders must own final decisions.
As the System, I want to support multi-cycle polling logic so decisions unfold in structured phases. |  |  |  |  | ● | CRS-23 | Repeatable decision frameworks. | Enables governance and repeatable playbooks.
As the System, I want to enforce governance, audit logging, and RBAC so trust and compliance are guaranteed. |  |  |  |  | ● | CRS-24 | Enterprise-grade control and traceability. | Non-negotiable for regulated organizations.
As the System, I want to calculate and assign Trinity Tokens (♡, 웃, ◬) so all forms of contribution are valued. |  |  |  |  | ● | CRS-25 | Fair recognition of time, expertise, and automation. | “Not all contributions are financial — but they still matter.”
MVP 3.0 — Simulation, Optimization & Evolution
As a Lead/Developer, I want to check out a cube into simulation mode so I can safely improve performance without impacting production. |  |  |  |  | ● | CRS-26 | Safe experimentation without risk. | Mirrors how senior engineers actually want to work.
As a Lead/Developer, I want to update cube code and rerun simulations so performance improvements can be validated objectively. |  |  |  |  | ● | CRS-27 | Proof that changes improve outcomes. | “Show me the metrics, not just the code.”
As the System, I want to replay upstream and downstream cube dependencies so changes are validated end-to-end. |  |  |  |  | ● | CRS-28 | Confidence that optimizations don’t break other parts. | Critical for modular architectures.
As the System, I want to compare simulation and production metrics so improvements are objectively measured. |  |  |  |  | ● | CRS-29 | Data-driven go/no-go decisions. | Prevents regressions disguised as improvements.
As a Lead/Developer, I want to approve or reject simulated cube changes so humans remain in control of evolution. |  |  |  |  | ● | CRS-30 | Human-in-the-loop governance. | Required before AI self-modifying systems.
As the System, I want to version every cube and dependency so rollback, audit, and lineage are possible. |  |  |  |  | ● | CRS-31 | Full traceability of system evolution. | “We need to know who changed what, and when.”
As the System, I want to attribute tokens to specific actions, cubes, and timestamps so contributors understand how value was created. |  |  |  |  | ● | CRS-32 | Transparent value attribution. | Builds long-term trust in the token model.
As a User or Lead/Developer, I want to flag or dispute token calculations so errors can be reviewed transparently. |  |  |  |  | ● | CRS-33 | Fairness and correction mechanisms. | Prevents resentment and loss of trust.
As the System, I want to assign lifecycle states to tokens so simulations and overrides remain safe. |  |  |  |  | ● | CRS-34 | Controlled financial and governance flow. | Required for audits and payouts.
As a Business Owner, I want standardized token definitions and valuation rules visible per session so outcomes are financially and culturally clear. |  |  |  |  | ● | CRS-35 | Executive clarity and adoption confidence. | “If leadership can’t explain it, it won’t scale.”

## Assumptions
# | Assumptions | Notes
A.01 | X: Y | Acceptance Criteria not Needed
A.02 | X: Y
A.03 | X: Y
A.04 | X: Y
A.05 | X: Y
A.06 | X: Y
A.07 | X: Y
A.08 | X: Y
A.09 | X: Y
A.10 | X: Y
A.11 | X: Y
A.12 | X: Y
A.13 | X: Y
A.14 | X: Y
A.15 | X: Y

## DesignTraceabilityMatrix
User Stories | CRS # | Dev Team | Design Input # | Specification Input: Target at Launch | Market Input: Stretch Target | Design Output # | Design Output: Definable / Mesaureable | Design Review # | Design Review Plan | Verification & Validation Plan | Test Run # | Test Issues | Test Issue Description | Design Transfer | Design Transfer Confirmation | Design Change | Design Change Description | .
🧊 Cube 1 — Session Join & QR (1,1,1)
As a Moderator, I want to create a polling session and generate a secure session link and QR code, so that participants can access the session instantly across devices. | CRS-01 | Software Platform/Web (SRS) | CRS-01.IN.SRS.001 | Generate a unique session URL and QR code within 2 seconds with 99.5% availability. | Branded, expiring QR codes with analytics and 99.9% availability. | CRS-01.OUT.SRS.001 | When a session is created, a scannable QR code and URL are displayed successfully. | DR-2026.01.01-DR.001
As a User, I want to join a polling session via QR code or link without authentication friction, so that I can participate immediately. | CRS-02 | Web/Mobile App (WRS) | CRS-02.IN.WRS.002 | Join via QR or link in three clicks or less with load time under five seconds. | One-tap join with device auto-detection and load time under two seconds. | CRS-02.OUT.WRS.002 | When a QR code is scanned, the session loads without login. | DR-2026.01.01-DR.001
As the System, I want to generate collision-free session IDs bound to QR codes, so that sessions cannot be spoofed or duplicated. | CRS-03 | Software Platform/Web (SRS) | CRS-03.IN.SRS.003 | Zero-collision UUID generation for all sessions. | Cryptographically signed and rotating session identifiers. | CRS-03.OUT.SRS.003 | Each new session is assigned a unique system ID automatically. | DR-2026.01.01-DR.001
As the System, I want to validate QR-based access and block expired or invalid sessions, so that unauthorized joins are prevented. | CRS-04 | Software Platform/Web (SRS) | CRS-04.IN.SRS.004 | Enforce expiration and validity rules with 100% accuracy. | Geo-fencing and abuse-detection heuristics. | CRS-04.OUT.SRS.004 | Attempts to join expired sessions are denied. | DR-2026.01.01-DR.001
🧊 Cube 2 — Text Submission Handler (1,1,2)
As the System, I want to support anonymous and identified participation modes, so that Moderators can choose the appropriate privacy level for each session. | CRS-05 | Software Platform/Web (SRS) | CRS-05.IN.SRS.005 | Moderator-controlled anonymity with role-based access control. | Hybrid anonymity with optional post-session reveal. | CRS-05.OUT.SRS.005 | In anonymous mode, no personally identifiable information is stored. | DR-2026.01.01-DR.001
As a Moderator, I want to open and close polling sessions deliberately, so that responses are collected only during the defined decision window. | CRS-06 | Software Platform/Web (SRS) | CRS-06.IN.SRS.006 | Poll state transitions propagate within one second. | Scheduled and automated open/close rules. | CRS-06.OUT.SRS.006 | When a poll is closed, responses stop immediately. | DR-2026.01.01-DR.001
As a User, I want to submit text-based responses to polling questions, so that I can clearly express ideas and feedback. | CRS-07 | Web/Mobile App (WRS) | CRS-07.IN.WRS.007 | Accept responses up to 500 characters with 99% success rate. | Rich text support with autosave and drafts. | CRS-07.OUT.WRS.007 | Submitted responses are saved and confirmed to the user. | DR-2026.01.01-DR.001
🧊 Cube 3 — Voice & Multi-Modal Input (1,1,3)
As the System, I want to securely store all responses with timestamps and encryption, so that data integrity and compliance are preserved. | CRS-08 | Software Platform/Web (SRS) | CRS-08.IN.SRS.008 | Encrypt responses at rest using AES-256 with timestamps. | Immutable append-only storage. | CRS-08.OUT.SRS.008 | Stored responses verify encryption and timestamp. | DR-2026.01.01-DR.001
As a User, I want to submit responses using voice instead of typing, so that participation is faster and more natural. | CRS-09 | AI/ML Platform (AIML) | CRS-09.IN.AIML.009 | Speech-to-text with word-error rate under 10% in English. | Multi-language speech-to-text with under 5% error rate. | CRS-09.OUT.AIML.009 | Spoken input appears as text in the response field. | DR-2026.01.01-DR.001
🧊 Cube 5 — Ranking Gateway (1,2,2)
As a User, I want to rank themes after polling closes, so that I can express what matters most to me. | CRS-12 | Web/Mobile App (WRS) | CRS-12.IN.WRS.012 | Ranking interface responds within 200 milliseconds. | Weighted and multi-criteria ranking options. | CRS-12.OUT.WRS.012 | Ranking order updates visually. | DR-2026.01.01-DR.001
As the System, I want to aggregate rankings deterministically, so that outcomes are fair and reproducible. | CRS-13 | Software Platform/Web (SRS) | CRS-13.IN.SRS.013 | Compute final rankings within three seconds. | AI-assisted consensus scoring. | CRS-13.OUT.SRS.013 | Final ordered priorities are computed correctly. | DR-2026.01.01-DR.001
🧊 Cube 6 — Decision Readiness (1,2,3)
As a Lead/Developer, I want to review ranked priorities with metadata, so that decisions are evidence-based. | CRS-14 | Software Platform/Web (SRS) | CRS-14.IN.SRS.014 | Display counts and timestamps for each theme. | Historical trend comparisons across sessions. | CRS-14.OUT.SRS.014 | Priorities and metadata are displayed correctly. | DR-2026.01.01-DR.001
As the System, I want to export session results, so that outcomes can be reused outside the platform. | CRS-15 | Software Platform/Web (SRS) | CRS-15.IN.SRS.015 | Export CSV within five seconds for up to 1,000 rows. | PDF, XLS, and API-based exports. | CRS-15.OUT.SRS.015 | Export file downloads successfully. | DR-2026.01.01-DR.001
🧊 Cube 7 — Live Prioritization (1,3,1)
As a Moderator, I want to enable live prioritization, so that consensus forms in real time during the session. | CRS-16 | Software Platform/Web (SRS) | CRS-16.IN.SRS.016 | Live ranking sync latency under 500 milliseconds. | Visual consensus alerts and animations. | CRS-16.OUT.SRS.016 | Live ranking updates propagate instantly. | DR-2026.01.01-DR.001
As a User, I want to see ranking updates live, so that collaboration feels responsive and shared. | CRS-17 | Web/Mobile App (WRS) | CRS-17.IN.WRS.017 | End-to-end update latency under one second. | Collaborative ranking tools and cues. | CRS-17.OUT.WRS.017 | User interface updates in real time. | DR-2026.01.01-DR.001
🧊 Cube 8 — Engagement & Tri-Coin Accounting (1,3,2)
As the System, I want to track engagement metrics, so that participation quality can be measured. | CRS-18 | Software Platform/Web (SRS) | CRS-18.IN.SRS.018 | Track joins, responses, and completion rates. | Predictive engagement analytics. | CRS-18.OUT.SRS.018 | Metrics appear in the dashboard. | DR-2026.01.01-DR.001
As the System, I want to calculate Shared Intention, Human Intelligence, and AI leverage, so that all contributions are valued. | CRS-19 | Software Platform/Web (SRS) | CRS-19.IN.SRS.019 | Deterministic off-chain token calculation. | On-chain settlement and payouts. | CRS-19.OUT.SRS.019 | Tokens are calculated at session close. | DR-2026.01.01-DR.001
🧊 Cube 9 — Deep Dives & Continuity (1,3,3)
As a Moderator, I want to launch deep-dive polling cycles, so that complex topics can be explored iteratively. | CRS-20 | Software Platform/Web (SRS) | CRS-20.IN.SRS.020 | Support up to three recursive cycles. | Unlimited AI-suggested cycles. | CRS-20.OUT.SRS.020 | New poll cycle is created on trigger. | DR-2026.01.01-DR.001
As a User, I want follow-up cycles to preserve context, so that my prior input remains relevant. | CRS-21 | Web/Mobile App (WRS) | CRS-21.IN.WRS.021 | Zero context loss across cycles. | Personalized follow-up prompts. | CRS-21.OUT.WRS.021 | Prior context remains visible. | DR-2026.01.01-DR.001
🧊 Cube 10 — Simulation, Governance & Evolution (2,2,2)
As a Lead/Developer, I want to override rankings with documented justification, so that accountability is preserved. | CRS-22 | Software Platform/Web (SRS) | CRS-22.IN.SRS.022 | Justification required and logged for every override. | Bias detection and peer review. | CRS-22.OUT.SRS.022 | Overrides require justification to proceed. | DR-2026.01.01-DR.001
As the System, I want to support multi-cycle polling logic, so that decisions unfold in structured phases. | CRS-23 | Software Platform/Web (SRS) | CRS-23.IN.SRS.023 | Deterministic state transitions across cycles. | Branching deep-dive paths. | CRS-23.OUT.SRS.023 | Next cycle initializes correctly. | DR-2026.01.01-DR.001
As the System, I want to enforce governance, audit logging, and role-based access, so that trust and compliance exist. | CRS-24 | Software Platform/Web (SRS) | CRS-24.IN.SRS.024 | Full action traceability by role. | SOC2 and ISO audit exports. | CRS-24.OUT.SRS.024 | Complete audit log is available. | DR-2026.01.01-DR.001
As a Lead/Developer, I want to check out a cube into simulation mode, so that I can improve performance safely. | CRS-25 | Software Platform/Web (SRS) | CRS-25.IN.SRS.025 | Isolated simulation environment per cube. | Parallel multi-cube simulation. | CRS-25.OUT.SRS.025 | Cube runs isolated from production. | DR-2026.01.01-DR.001
As a Lead/Developer, I want to modify cube code and rerun simulations, so that improvements can be validated. | CRS-26 | Software Platform/Web (SRS) | CRS-26.IN.SRS.026 | Baseline vs variant metric comparison. | AI-assisted optimization hints. | CRS-26.OUT.SRS.026 | Metrics comparison is displayed. | DR-2026.01.01-DR.001
As the System, I want to replay upstream and downstream cube dependencies, so that changes are validated end-to-end. | CRS-27 | Software Platform/Web (SRS) | CRS-27.IN.SRS.027 | Deterministic dependency replay. | Parallel dependency graph simulation. | CRS-27.OUT.SRS.027 | No regressions are detected. | DR-2026.01.01-DR.001
As the System, I want to compare simulation and production metrics, so that improvements are objectively measured. | CRS-28 | Software Platform/Web (SRS) | CRS-28.IN.SRS.028 | Latency and cost deltas calculated. | Predictive impact scoring. | CRS-28.OUT.SRS.028 | Improvement deltas are displayed. | DR-2026.01.01-DR.001
As a Lead/Developer, I want to approve or reject simulated cube changes, so that humans remain in control. | CRS-29 | Software Platform/Web (SRS) | CRS-29.IN.SRS.029 | Manual approval gate enforced. | Reputation-weighted approvals. | CRS-29.OUT.SRS.029 | Approved changes are promoted. | DR-2026.01.01-DR.001
As the System, I want to version every cube and dependency, so that rollback and audits are possible. | CRS-30 | Software Platform/Web (SRS) | CRS-30.IN.SRS.030 | Immutable version graph per cube. | AI rollback recommendations. | CRS-30.OUT.SRS.030 | Version history is visible. | DR-2026.01.01-DR.001
As the System, I want to preserve Tri-Coin integrity across simulations, so that value accounting is never corrupted. | CRS-31 | Software Platform/Web (SRS) | CRS-31.IN.SRS.031 | Token calculations remain invariant. | Fairness optimization engine. | CRS-31.OUT.SRS.031 | Token parity is verified. | DR-2026.01.01-DR.001
As the System, I want to generate AI-proposed cube improvements, so that evolution accelerates. | CRS-32 | AI/ML Platform (AIML) | CRS-32.IN.AIML.032 | At least one AI-generated variant per cube. | Multi-agent self-optimization. | CRS-32.OUT.AIML.032 | Ranked AI proposals are displayed. | DR-2026.01.01-DR.001
As a Lead/Developer, I want to select which AI-generated cube version to adopt, so that judgment remains human-guided. | CRS-33 | Software Platform/Web (SRS) | CRS-33.IN.SRS.033 | Human selection required before promotion. | Delegated trust thresholds. | CRS-33.OUT.SRS.033 | Selected cube version is promoted. | DR-2026.01.01-DR.001
As the System, I want to gradually automate cube evolution under guardrails, so that safe self-optimization emerges. | CRS-34 | AI/ML Platform (AIML) | CRS-34.IN.AIML.034 | Guardrail-constrained autonomy. | Fully self-healing architecture. | CRS-34.OUT.AIML.034 | Autonomous cycles are logged. | DR-2026.01.01-DR.001
As the System, I want to evolve the entire cube lattice coherently, so that the platform improves as a living system. | CRS-35 | AI/ML Platform (AIML) | CRS-35.IN.AIML.035 | Coordinated cube evolution. | Self-directed system intelligence. | CRS-35.OUT.AIML.035 | System-wide gains are measured. | DR-2026.01.01-DR.001

## Design Changes
Design Change | Design Change Description | Design Change Approvals: 3 Letter Initials
DC.001_2020.08.30_HRS.001
DC.002_2020.08.30_HRS.001

## v1
S.No | Core Feature | Task | Froentend | Backend | AI | DevOps | Mapped Functions
1 | Project Setup & Kickoff | - Project kickoff & onboarding - Final requirement walkthrough & scope freeze - Architecture finalization (Web, AI, data flow) - Repo setup (FE/BE), branching strategy - Environment setup (local, dev) - Coding standards & review process | 1 | 2 | 1 | 2 | Delivery foundation
2 | Session Creation & Access | - Create session (Host) - Generate unique session ID - QR code & shareable link - Session lifecycle states (draft/open/close) - Join session via QR/link (User) | 3 | 5 | 0 | 0 | Session CRUD, QR generation, join flow
3 | Question Preparation & Voting | - Free-form question entry (≤500 chars) - Draft auto-save - Finalize questions - Open/close voting - Real-time voting status updates | 4 | 5 | 0 | 0 | Question management, voting state machine
4 | User Response Collection (Multi-Modal) | - Text response submission - Voice input via Web Audio API - Speech-to-text handling - Anonymous participation mode - Input validation & limits | 5 | 4 | 1 | 0 | Response ingestion, accessibility
5 | AI Theme Generation | - Theme 01 categorization (Support / Risk / Neutral) - Theme 02 sub-clustering - Theme 03 refinement (optional) - Embeddings & vector storage (Pinecone) - Accuracy/confidence scoring (~80%) | 2 | 6 | 14 | 0 | AI theming, clustering, vector search
6 | Theme Visualization & Review | - Theme listing UI - Accordion/category views - Accuracy % display - User vs Group view toggle - Refresh & polling | 4 | 2 | 1 | 0 | Insights visualization
7 | Prioritization & Ranking | - Drag-and-drop ranking (User) - Real-time rank sync (WebSockets) - Rank aggregation logic - Lock prioritization | 4 | 4 | 0 | 1 | Live prioritization engine
8 | Host Overrides & Governance | - Host override of final ranks - Justification capture - Immutable audit logs - Bias/override tracking | 2 | 3 | 0 | 0 | Governance & audit trail
9 | Deep Dive Cycles | - Select 1–3 themes - Auto-generate follow-up questions - Repeat response → theme → rank cycle - Limit cycles to 3 | 4 | 4 | 6 | 0 | Recursive session flow
10 | Reports & Exports | - Preliminary summary reports (Team) - Full detailed exports (Host/User) - CSV/TXT via Pandas - GDPR PII masking | 3 | 4 | 1 | 0 | Reporting & data export
11 | Analytics & Engagement Metrics | - Participation metrics - Active time tracking - Token summaries - Session-level dashboards | 3 | 4 | 1 | 0 | Analytics & insights
12 | Trinity Tokens | - Minutes calculation - Quality scoring - AI impact calculation - Profile balance display | 2 | 4 | 1 | 0 | Token accounting (off-chain)
13 | Payments (One-Time, Stripe) | - Stripe checkout (one-time) - Unlock paid reports - Receipt handling - Freemium limits | 2 | 3 | 0 | 0 | Monetization
14 | Auth, Security & Compliance | - JWT auth & RBAC - Anonymous mode - GDPR consent & deletion - WCAG compliance | 1 | 4 | 0 | 0 | Security & privacy
15 | DevOps & Deployment | - Environment setup - FastAPI deployment - Kubernetes (single-tenant) - Monitoring & logging | 0 | 2 | 0 | 5 | Infrastructure
16 | Quality Assurance | - Test plan & test case preparation - Functional testing (Host / Team / User flows) - AI output validation (theme accuracy, summaries) - Real-time flow testing (WebSockets, ranking sync) - Cross-browser & mobile web testing - Regression testing before releases - UAT support & bug verification | 5 | 5 | 5 | 0 | End-to-end quality validation
17 | Project Management | - Requirement analysis & scope confirmation - Project planning & backlog grooming - Daily standups & coordination - Dependency & risk management (AI + live sessions) - Stakeholder demos & reviews - Timeline & milestone tracking - Release coordination & handover | 4 | 4 | 4 | 3 | Delivery governance
|  |  | 49 | 65 | 35 | 11
|  | Total Man Days | 160

## v2
S No | Module | Tasks | Estimated Man-Days
|  |  | Frontend | Backend Services | AI | DevOps
1.1 | Frontend, UI/UX | - UI/UX and screen designs - Design & Implement Multi-Device Session Onboarding & QR JoinBuild a responsive React/React Native UI that dynamically adapts to both web and mobile users. Integrate qrcode generation for session onboarding, ensuring seamless deep-linking across platforms. Implement progressive UI states for session not found, expired, or already joined. Coordinate state sync between Host PC display and mobile device control, supporting real-time participant status and notifications. | 8 | 3 | 0 | 0
1.2 |  | Drag-and-Drop Voting & Prioritization FlowsDevelop React DnD-based components to enable fluid drag-and-drop prioritization for theme ranking and session workflows. Handle touch and mouse events, real-time updates via Socket.io, and visual feedback for rank changes. Ensure keyboard accessibility and ARIA support for all DnD flows. Integrate live visual indicators for consensus state and override notifications. | 7 | 3 | 1 | 0
1.3 |  | Voice/Multimodal Input & Accessibility EnhancementsImplement robust text and voice input support using Web Audio API and browser-compatible STT libraries. Build language selector integrated with Google Translate API for 33 languages, and provide live translation feedback. Adhere strictly to WCAG for all inputs, including ARIA, color contrast, and screen reader flows. Implement modal dialogs and tooltips to guide users on multi-modal features. | 7 | 2 | 1 | 0
1.4 |  | Theme Visualization & Deep-Dive NavigationDevelop theme accordion components for presenting clustered themes and subthemes, with badge indicators for clustering accuracy. Implement Host-driven “deep dive” cycle navigation with context-preserving breadcrumbs and visually distinct cycle progress bars. Ensure smooth transitions between session cycles and detailed views for subtheme discussions. | 6 | 2 | 1 | 0
1.5 |  | Profile & Wallet Dashboard for Token RewardsCreate interactive profile and wallet dashboard views to display live Trinity Token balances (♡, 웃, ◬), transaction history, and recent earnings. Integrate wallet connect options, real-time token swap status, and analytics visualizations for user engagement and session impact. Provide feedback/status for token transfers and reward redemption. | 7 | 2 | 1 | 0
1.6 |  | Export, Paywall, & Notification UIBuild a unified export/download center for redacted and full reports, with real-time export progress and clear access restrictions. Implement paywall components with Stripe integration, supporting micro-payments and report upgrades. Integrate Firebase push notification opt-in and a user notification center for session/event updates, payment, and deadlines. | 5 | 3 | 0 | 0
2.1 | Backend | Session Service: CRUD, State, and Participant ManagementDesign and build a FastAPI microservice for full session lifecycle: creation, update, deletion, status transitions (prep, open, closed, archived). Implement participant join/leave tracking with unique session IDs and device type detection. Ensure stateful tracking and broadcast of session changes via WebSocket channels. Integrate with PostgreSQL for structured storage. | 2 | 6 | 1 | 0
2.2 |  | Voting, Response Handling, and Data SyncDevelop endpoints for question management (prep/open/close), voting response submission (multi-modal: text, voice, future video), and batch response retrieval. Ensure MongoDB storage for unstructured response payloads and Redis caching for real-time state. Support both synchronous and queued (Kafka) processing for large-scale sessions. | 2 | 8 | 0 | 0
2.3 |  | AI Processing Orchestration ServiceBuild a scalable orchestration layer that triggers AI theme clustering and summarization workflows upon vote close. Handle embedding extraction, KMeans clustering, and Hugging Face T5 summarization via internal job queue. Store clustering jobs, results, and logs for audit and retraining. Return status and results to frontend via WebSockets. | 0 | 7 | 3 | 0
2.4 |  | Prioritization & Blockchain Override Logging ServiceImplement backend logic to aggregate user drag-and-drop ranks (median calculation) and manage Host override submissions. Securely log all override justifications and actions on-chain using web3.py to Ethereum/Quai. Provide real-time override audit trails via API and ensure error handling for blockchain transaction failures and retries. | 1 | 8 | 2 | 0
2.5 |  | Export & Report Generation ServiceDevelop export pipelines to generate redacted and full reports in CSV/PDF via Pandas, supporting filtering by user role and masking of PII. Enable scheduled report generation and delivery through email, Slack, or download links. Integrate payment access checks for paywalled content. | 1 | 3 | 1 | 0
2.6 |  | Analytics & Engagement Dashboard ServiceBuild FastAPI service endpoints for engagement, participation, and ROI analytics—leveraging Matplotlib for chart generation and ML regression for ROI prediction. Provide role-based summaries and exportable analytics in multiple formats. | 2 | 3 | 2 | 0
2.7 |  | Integration and Webhook Management ServiceImplement OAuth2 and webhook endpoints for Slack, Teams, and CRM integrations. Provide secure token storage, event mapping, and notification routing for external services. Log all integration activity for security audit and troubleshooting. | 1 | 3 | 0 | 0
3.1 | Database | PostgreSQL Schema Design & ShardingDesign normalized, scalable schemas for sessions, users, questions, tokens, and audit trails. Implement sharding logic to support 1M+ concurrent users, optimize for session lookup and join performance. Integrate schema migration tooling (Alembic or similar) and set up initial data seeding for dev/test environments. | 0 | 3 | 0 | 0
3.2 |  | MongoDB for Unstructured Response StorageDesign flexible, performant collections for multi-modal user responses and theme artifacts. Implement indexing for efficient search, pagination, and theme linkage. Build archiving and data lifecycle management (e.g., TTL indexes, scheduled cleanups). | 0 | 3 | 0 | 0
3.3 |  | Pinecone Vector DB Integration for Semantic SearchSet up Pinecone instance(s) for storage and retrieval of embedding vectors. Implement backend service methods to store, update, and query user/input embeddings. Support nearest-neighbor search for theme clustering and validate performance at scale. | 0 | 3 | 2 | 0
3.4 |  | Redis for Real-Time State CachingConfigure Redis cluster for session state, participant presence, and short-term analytics caching. Ensure eviction policy, monitoring, and auto-recovery. Integrate with backend microservices for low-latency state reads/writes and distributed locking where needed. | 0 | 3 | 0 | 0
4.1 | AI | NLP Pipeline: Embedding, Clustering, SummarizationBuild AI workflows to process raw user input, generate dense embeddings using Hugging Face models, cluster responses using KMeans, and generate summaries per theme using T5. Tune and validate clustering for accuracy >80% cosine sim. Document and modularize all AI code for future retraining and hyperparameter adjustment. | 0 | 1 | 15 | 0
4.2 |  | Prompt Engineering & Auto-Question GenerationDevelop prompt templates and workflows to automatically generate follow-up questions and recursive deep-dive prompts. Implement auto-tuning and feedback loop for prompt quality, capturing data for ongoing model improvement. | 0 | 1 | 10 | 0
4.3 |  | AI Service API & ScalingExpose AI pipeline via internal REST endpoints, supporting async job dispatch, status polling, and bulk result retrieval. Build autoscaling scripts or configs to ensure <1s inference at peak load. Integrate error logging and fallback mechanisms for model/server failures. | 0 | 2 | 5 | 0
4.4 |  | AI Bias & Quality MonitoringImplement pipeline to log, monitor, and review clustering/summarization outcomes for fairness and accuracy. Build dashboard for error rates, outliers, and bias flagging. Schedule regular retraining using diverse datasets. | 0 | 1 | 5 | 0
5.1 | Blockchain, Web3js | Smart Contract Development & DeploymentDesign and deploy Ethereum/Quai contracts for Trinity Tokens (♡, 웃, ◬), supporting mint, transfer, burn, and override event logging. Write and test contracts in Solidity/Vyper, covering gas optimization and role-based permissions. | 0 | 1 | 0 | 0
5.2 |  | Token Minting and Reward Logic IntegrationImplement backend logic using web3.py to trigger on-chain minting on key user actions (vote, deep-dive, export). Optimize for batch minting to minimize gas fees. Handle on-chain/off-chain event reconciliation for dev/test environments. | 1 | 5 | 0 | 0
5.3 |  | Wallet Integration & Swap FunctionalityDevelop frontend wallet connection and transaction UI for QUAI/Ethereum (e.g., MetaMask, WalletConnect). Enable in-app swap of ◬ to QUAI/QI, with real-time status polling, error messages, and user confirmation flows. | 5 | 2 | 0 | 0
5.4 |  | Blockchain Audit & AnalyticsAggregate on-chain events for reporting in dashboards. Provide backend APIs for audit log access, reconciliation, and export. Build automated tests for all blockchain flows, ensuring security and transparency. | 1 | 3 | 0 | 0
6.1 | API | RESTful Endpoint Development and TestingDesign and build FastAPI endpoints for sessions, voting, theming, ranking, report export, and token minting. Enforce JWT authentication, RBAC, input validation, and error handling on all endpoints. Write comprehensive unit and integration tests, covering both successful and edge-case scenarios. | 0 | 5 | 0 | 0
6.2 |  | WebSocket & Real-Time Update InfrastructureImplement robust Socket.io/WebSocket server for broadcasting real-time session status, theme results, ranking changes, and notifications. Integrate with frontend for live updates, disconnection handling, and reconnection logic. | 2 | 5 | 0 | 0
6.3 |  | API Documentation and Developer PortalGenerate and maintain Swagger/OpenAPI docs for all REST endpoints, detailing roles, auth flows, and error codes. Develop simple developer portal or static docs site for third-party integrators (Slack, CRM, etc). | 1 | 4 | 0 | 0
6.4 |  | Rate Limiting, Security & GDPR ComplianceImplement per-user and per-endpoint rate limiting, ensure secure data access, and build GDPR consent and data deletion workflows. Provide audit logs for all sensitive actions and role changes. | 1 | 6 | 0 | 0
7.1 | Integrations | Firebase Push Notification ServiceSet up Firebase project, configure backend to dispatch push notifications for session events, deadlines, and payment updates. Build frontend hooks for opt-in/out, notification display, and read/unread tracking. | 2 | 4 | 0 | 1
7.2 |  | Stripe Payments & Paywall ServiceIntegrate Stripe API for session upgrades and report micro-payments. Implement backend payment status callbacks, receipt generation, and access control. Build frontend paywall UI and manage purchase state across app. | 4 | 5 | 0 | 2
7.3 |  | Slack/CRM Webhook and OAuth IntegrationEnable connection and disconnection of Slack/CRM accounts via OAuth2. Build webhook endpoints for report/summary push, and develop frontend UI for integration management and status feedback. | 2 | 4 | 0 | 2
7.4 |  | Accessibility & Translation InfrastructureIntegrate Google Translate API for 33 languages, speech-to-text APIs, and frontend toggles for language selection. Implement full internationalization and test UI/UX in RTL and LTR scripts. | 4 | 2 | 1 | 1
9.1 | DevOps | CI/CD Pipeline Setup & AutomationDevelop automated build, test, and deploy pipelines in GitHub Actions. Configure Dockerfiles, environment variable management, secrets rotation, and branch-based deployment triggers. Ensure staged deployment for MVP → Full Release. | 0 | 0 | 0 | 5
9.2 |  | Kubernetes (EKS) Cluster & Auto-Scaling ConfigurationProvision AWS EKS clusters, implement auto-scaling policies, configure persistent storage, and set up managed sharded PostgreSQL, MongoDB, Pinecone, and Redis services. Develop Helm charts for microservice deployment, rolling updates, and zero-downtime scaling. | 0 | 0 | 0 | 6
9.3 |  | Monitoring, Logging, and AlertingIntegrate Prometheus/Grafana for real-time metrics, Sentry for error reporting, and centralized logging for all services. Build custom dashboards to track user engagement, system health, and cost. Set up alerting for performance anomalies and budget overruns. | 0 | 0 | 0 | 5
9.4 |  | Backup, Archival, and Data CompressionAutomate nightly DB backups, configure data archival policies for MongoDB/Pinecone, and implement Snappy (or similar) data compression for long-term storage. Routinely test restore procedures for disaster recovery. | 0 | 0 | 0 | 4
8.1 | QA | Manual testing, feedback and bug fixes | 5 | 5 | 5 | 0
8.1 | Project Management | Conduct Scrum, Organize calls to demo and get feedback to deliver | 5 | 5 | 5 | 5
|  | Total Days | 82 | 126 | 61 | 31
|  | Total Estimated Days | 300

## v3
MVP 1.0 Working Prototype
S.No | Core Feature | Froentend | Backend | AI | DevOps
1 | Project Setup & Kickoff | 1 | 2 | 1 | 1
2 | Session Creation & Access | 3 | 4 | 0 | 0
3 | Question Preparation & Voting | 3 | 4 | 0 | 0
4 | User Responses (Text Only) | 4 | 3 | 0 | 0
5 | AI Theme Generation (Basic) | 1 | 3 | 8 | 0
6 | Theme Visualization | 3 | 2 | 0 | 0
7 | Ranking (Auto, Non-Real-Time) | 2 | 3 | 0 | 0
8 | Reports & Export (CSV) | 2 | 2 | 0 | 0
9 | Auth & Security | 1 | 3 | 0 | 0
10 | DevOps (Single Env) | 0 | 1 | 0 | 3
11 | QA | 2 | 2 | 2 | 1
12 | Project Management | 2 | 2 | 2 | 2
Totals |  | 24 | 31 | 13 | 7
MVP 2.0 Usability, Intelligence & Collaboration
S.No | Core Feature | Froentend | Backend | AI | DevOps
1 | Multi-Modal Responses (Voice) | 1 | 1 | 4 | 0
2 | AI Enhancements (Theme-02) | 1 | 2 | 7 | 0
3 | Theme Visualization (Enhanced) | 3 | 2 | 0 | 0
4 | Live Prioritization (WebSockets) | 3 | 3 | 0 | 2
5 | Analytics & Metrics | 3 | 4 | 1 | 0
6 | Reporting & Compliance | 1 | 2 | 1 | 0
7 | DevOps Upgrade (K8s) | 0 | 1 | 0 | 4
8 | QA (Regression + Realtime) | 2 | 2 | 2 | 0
9 | Project Management | 2 | 2 | 2 | 0
Totals |  | 16 | 19 | 17 | 6
Total Man Days |  | 58
MVP 3.0 Governance, Monetization & Production Readiness
S.No | Core Feature | Froentend | Backend | AI | DevOps
1 | Deep Dive Cycles | 4 | 4 | 2 | 0
2 | Governance & Audit | 2 | 4 | 0 | 0
3 | Trinity Tokens | 1 | 2 | 1 | 0
4 | Payments (Stripe) | 1 | 2 | 0 | 0
5 | DevOps Hardening | 0 | 1 | 0 | 1
6 | QA & Final Release | 1 | 1 | 0 | 0
|  | 9 | 14 | 3 | 1
| Total Man Days | 27