## Legend + Assumptions
Innovation Project — Customer Requirement Specification (CRS)
Governs an R-Core innovation project run on the eXeL AI platform. ID grammar follows the AMTS Design Traceability Matrix.
HOW TO USE
Blue text | Hardcoded input — edit these.
Yellow fill | Assumption to confirm. Every one is a placeholder until you set it.
Black text | Formula. Do not overwrite.
ID GRAMMAR
CRS-##.IN.SRS.### | Design input — what the customer/business requires.
CRS-##.OUT.SRS.### | Design output — the definable, measurable result.
DR-YYYY.MM.DD-DR.### | Design review.
TR-YYYY.MM.DD-TR.### | Test run.
TR.###_YYYY.MM.DD_IS.### | Test issue raised against a test run.
DT.###_YYYY.MM.DD_PRS.### | Design transfer.
DC.###_YYYY.MM.DD_PRS.### | Design change.
PROGRAM ASSUMPTIONS
Assumption | Value | Source
Projects in program | 9 | Stated by user
Total program funding ($) | 9000000 | Stated by user
Baseline duration per project (months) | 9 | Stated by user
Target compressed duration (months) | 7 | Stated by user
Working days per month | 21 | ASSUMPTION — confirm
Working hours per day | 8 | ASSUMPTION — confirm
Early-delivery pool, minimum (% of program) | 10% | Stated by user — floor
Early-delivery pool, target (% of program) | 11.11% | Stated by user — $1M on $9M
Share of pool to delivery team (%) | 60% | PROPOSAL — see CRS-17
Share of pool to gate approvers (%) | 25% | PROPOSAL — see CRS-17
Share of pool to risk market (%) | 15% | PROPOSAL — see CRS-17
Clawback reserve held to launch (%) | 30% | PROPOSAL — see CRS-18

## Incentive Model
Early-Delivery Incentive — self-funding from avoided burn
The pool is paid out of R&D burn that was budgeted and not spent. The sponsor's return is the revenue pulled forward, which is not consumed by the pool.
Program burn rate ($/month) | 1000000
Program burn rate ($/day) | 47619.0476
Program burn rate ($/hour) | 5952.381
Program burn rate ($/min) — MoT | 99.2063
Per-project burn rate ($/min) | 11.0229
Months delivered early | 2
Burn avoided ($) | 2000000
Pool at minimum rate ($) | 1800000
Pool at target rate ($) | 1999800
Pool as % of burn avoided (target) | 99.99%
Sponsor net on burn alone ($) | 200
Delivery team share ($) | 1199880
Gate approver share ($) | 499950
Risk market share ($) | 299970
Split check (must equal pool) | 1999800
Note: target pool at 2 months early equals the burn avoided exactly. Sponsor return comes from revenue displacement, not from burn. See CRS-17. | 1399860
Held to launch, at risk ($) | 599940

## Design Matrix
Product Requirements: Design Traceability Matrix — Innovation Project
Plan Stage: Customer User Stories + Customer Requirement Specs ¦ Develop Stage: Team Specification # + Design Output #
Gate | Dev Team | Design Input # | Specification Input: Target at Launch | Market Input: Stretch Target | Design Output # | Design Output: Definable / Measurable | Source
G1 | Software | CRS-75.IN.SRS.040 | Platform is the sole system of record for G1-G7 progression; a gate state that exists only in a deck or email is not a gate state. | External PM tools read gate state from the platform API rather than holding their own. | CRS-75.OUT.SRS.040 | 100% of gate transitions carry a platform event; zero reconstructed from documents. | Vision 2525 design
G1 | Software | CRS-76.IN.SRS.041 | A deliverable advances only when its bound API function completes with a valid payload. No manual status field exists. | Function completion auto-drafts the gate review packet. | CRS-76.OUT.SRS.041 | Zero writable status fields in schema; deliverable state is a fold over the event log, reproducible on replay. | Vision 2525 design
G1 | Software | CRS-77.IN.SRS.042 | Gate transition blocked while any DACI-designated Approver has not signed. Reviewers are advisory and non-blocking. | Approver absence auto-escalates to the Steering Team after a set interval. | CRS-77.OUT.SRS.042 | No gate closes with an outstanding required Approver; escalation fires within the configured interval. | AMTS DACI table
G1 | Software | CRS-78.IN.SRS.043 | All state changes recorded in an append-only event log. Gate Review History is a query over that log. | Any past moment reconstructable for audit or gate review. | CRS-78.OUT.SRS.043 | Replay to any timestamp reproduces the state shown at that time; audit trail and state cannot disagree. | Vision 2525 design
G2 | UX / ID | CRS-79.IN.SRS.044 | Project state renders as a 3x3x3 cube whose cells fill as deliverables are approved. | Portfolio view shows all projects as cubes at a glance. | CRS-79.OUT.SRS.044 | A user identifies stage and blocking gate from the cube alone, without reading text. | Cube Analysis
G2 | Software | CRS-80.IN.SRS.045 | Deliverable groupings always tile exactly 27 cells with every group face-connected. | Partition strategy selectable per project for visual variety. | CRS-80.OUT.SRS.045 | Validator rejects any configuration not summing to 27 or containing a disconnected group; failure throws rather than renders. | Cube Analysis
G2 | Software | CRS-81.IN.SRS.046 | Any authenticated user may submit a risk prediction against any project, gate, or item, regardless of assignment. | External partners and customers may submit under a restricted scope. | CRS-81.OUT.SRS.046 | Submission accepted from users with no role on the target project; median submission time under 60 seconds. | Stated by user
G3 | AI/ML | CRS-82.IN.SRS.047 | Submitted risks are clustered into themes and returned for team voting. | Themes proposed live as submissions arrive rather than on close. | CRS-82.OUT.SRS.047 | 1,000,000 responses themed in under 60 seconds; identical input produces identical themes. | Existing CRS scale target
G3 | Software | CRS-83.IN.SRS.048 | Predictions resolve as materialized, mitigated, superseded, not-borne-out, or unresolvable. Mitigated pays identically to materialized. | Resolution proposed automatically from gate evidence, confirmed by a human resolver. | CRS-83.OUT.SRS.048 | Payout for mitigated equals materialized at equal lead time and specificity; verified by test case. | Prevention paradox fix
G3 | Software | CRS-84.IN.SRS.049 | Predictor, actioner, and resolver enforced as distinct identities on any prediction. Predictions require a stake. | Stake size set by the predictor as a confidence signal. | CRS-84.OUT.SRS.049 | Zero predictions resolve where any two roles share an identity; 100% of scored predictions carry a stake. | Anti-gaming control
G3 | Software | CRS-85.IN.SRS.050 | Every item carries planned and actual time start and time stop. No item exists without both planned values. | Actuals captured from function events rather than self-reported. | CRS-85.OUT.SRS.050 | 100% of items have planned start and stop at gate entry; actuals present for all closed items. | Stated by user
G4 | Finance / FP&A | CRS-86.IN.SRS.051 | Durations and costs render with the stage tolerance band: +/-60% Concept, +/-40% Plan, +/-20% Develop, +/-10% Qualify, +/-5% Launch. | Band narrows continuously from evidence rather than stepping at gates. | CRS-86.OUT.SRS.051 | No point estimate rendered without its band; failure to tighten by the next gate raises a flag. | AMTS BC Development slide
G4 | Software | CRS-87.IN.SRS.052 | Moving any date moves all dependent dates and downstream financials right, including budget calendar, with no manual re-entry. | Cascade previewed before commit, showing blast radius across projects. | CRS-87.OUT.SRS.052 | Date of first revenue is derived, never entered; a slip updates NPV, IRR, FTE ramp and budget within one refresh. | Stated by user
G4 | Finance / FP&A | CRS-88.IN.SRS.053 | Cost of elapsed time reported to $/min at portfolio and project level, split into burn and revenue displacement. | Open decisions show accrued cost since they opened. | CRS-88.OUT.SRS.053 | Both figures shown separately and never summed silently; portfolio and per-project rates on every project view. | Stated by user - MoT
G4 | Software | CRS-89.IN.SRS.054 | Cross-project critical path derivable from the dependency graph on demand. | Graph distinguishes hard dependencies from assumed ones. | CRS-89.OUT.SRS.054 | For 400 projects, the set determining the portfolio date is listable in a single view. | Stated by user
G5 | Business Mgmt | CRS-90.IN.SRS.055 | Schedule baseline for incentive calculation locked at G2 by an Approver outside the delivery team, immutable thereafter. | Baseline lock requires a second approver from Finance. | CRS-90.OUT.SRS.055 | Zero baselines edited after lock; zero locked by an identity in the receiving team. | Anti-sandbagging control
G5 | Business Mgmt | CRS-91.IN.SRS.056 | Project Upside against the locked baseline funds a pool of at least 10% of program value per month early (target 11.1%, $1M per month on $9M), shared across delivery team, gate approvers, and risk market participants. | Pool auto-splits by measured contribution rather than fixed shares. | CRS-91.OUT.SRS.056 | Pool never exceeds burn avoided; approver share non-zero wherever review latency contributed to the saving. | Stated by user
G5 | Business Mgmt | CRS-92.IN.SRS.057 | Upside reward scales with critical-path contribution: early delivery that unblocks a downstream team earns a multiplier over early delivery off the critical path. | Multiplier previewed before a team commits to a compression. | CRS-92.OUT.SRS.057 | Multiplier computed from the dependency graph, not assigned by hand; off-critical-path upside pays base rate only. | Stated by user
G6 | HR Planning | CRS-93.IN.SRS.058 | Intelligence load tracked across AI, SI, and HI contribution per team, with sustained human-load thresholds acting as a burnout guard that reduces or voids upside payout. | Load trend predicts burnout risk before the threshold is crossed. | CRS-93.OUT.SRS.058 | Upside earned above the human-load threshold is withheld pending review; guard is enforcing, not advisory. SI measurement rule PENDING DEFINITION. | Stated by user

## Verification
Qualify Stage: Design Matrix — Design Review # + Test Run #
One row per verification event. Fill as reviews and test runs occur.
Design Input # | Design Review # | Design Review Plan | Verification & Validation Plan | Test Run # | Test Issues | Test Issue Description
CRS-05.IN.SRS.005 | DR-2026.09.14-DR.001 | Theming determinism review with AI/ML + Software | Replay 1M-response corpus 3x; compare theme sets byte-for-byte | TR-2026.09.28-TR.001 | TR.001_2026.09.28_IS.001 | Run 3 produced 41 themes vs 40; non-determinism traced to provider ordering
^ example row — replace

## Transfer + Change
Launch Stage: Design Matrix — Design Transfer + Design Change
Design Input # | Design Transfer | Design Transfer Confirmation | Design Change | Design Change Description
CRS-10.IN.SRS.010 | DT.001_2026.11.02_PRS.001 | Cascade engine handed to Ops, signed by R&D | DC.001_2026.11.18_PRS.001 | Budget calendar added to cascade after FP&A review
^ example row — replace

## Gate Map
Gate Map — 27 cells across G1-G7
partition(7) yields 4,4,4,4,4,4,3. CRS entries occupy cells; remaining cells are filled by AMTS Recommended items and Design Matrix artifacts.
Gate | Stage | Cells (from partition) | CRS assigned | Cells unassigned
G1 | Concept | 4 | 4 | 0
G2 | Plan | 4 | 3 | 1
G3 | Develop | 4 | 4 | 0
G4 | Qualify | 4 | 4 | 0
G5 | Launch | 4 | 3 | 1
G6 | Maximize | 4 | 1 | 3
G7 | Retire / EOL | 3 | 0 | 3
| TOTAL | 27 | 19 | 8
| Cube check (must be 27) | OK